## RTM
Project Name | TutorialNinja(Front-end)
Client | TutorialNinja
Created By | Sumit Rane
Creation Date | 2025-04-01
Approval Date | 2025-04-02
Requirement ID | Requirement Description | Test Scenario ID | Test Scenario Description | Test Case IDs | Test Result | Defect ID | Defect Status
1.1 | Register | TS_001 | Validate the working of Register Account functionality | TC_RF_001 | Pass
|  |  |  | TC_RF_002 | Pass
|  |  |  | TC_RF_003 | Pass
|  |  |  | TC_RF_004 | Pass
|  |  |  | TC_RF_005 | Pass
|  |  |  | TC_RF_006 | Pass
|  |  |  | TC_RF_007 | Pass
|  |  |  | TC_RF_008 | Pass
|  |  |  | TC_RF_009 | Pass
|  |  |  | TC_RF_010 | Pass
|  |  |  | TC_RF_011 | Pass
|  |  |  | TC_RF_012 | Pass
|  |  |  | TC_RF_013 | Pass
|  |  |  | TC_RF_014 | Fail | DEF_009 | Open
|  |  |  | TC_RF_015 | Pass
|  |  |  | TC_RF_016 | Pass
|  |  |  | TC_RF_017 | Fail | DEF_010 | Open
|  |  |  | TC_RF_018 | Pass
|  |  |  | TC_RF_019 | Pass
|  |  |  | TC_RF_020 | Pass
|  |  |  | TC_RF_021 | Pass
|  |  |  | TC_RF_022 | Pass
|  |  |  | TC_RF_023 | Pass
|  |  |  | TC_RF_024 | Pass
1.2 | Login | TS_002 | Validate the working of Login functionality | TC_LF_001 | Pass
|  |  |  | TC_LF_002 | Pass
|  |  |  | TC_LF_003 | Pass
|  |  |  | TC_LF_004 | Pass
|  |  |  | TC_LF_005 | Pass
|  |  |  | TC_LF_006 | Pass
|  |  |  | TC_LF_007 | Pass
|  |  |  | TC_LF_008 | Pass
|  |  |  | TC_LF_009 | Pass
|  |  |  | TC_LF_010 | Pass
|  |  |  | TC_LF_011 | Blocked
|  |  |  | TC_LF_012 | Pass
|  |  |  | TC_LF_013 | Pass
|  |  |  | TC_LF_014 | Pass
|  |  |  | TC_LF_015 | Blocked
|  |  |  | TC_LF_016 | Blocked
|  |  |  | TC_LF_017 | Pass
|  |  |  | TC_LF_018 | Pass
|  |  |  | TC_LF_019 | Pass
|  |  |  | TC_LF_020 | Blocked
|  |  |  | TC_LF_021 | Pass
1.3 | Logout | TS_003 | Validate the working of Logout functionality | TC_LG_001 | Pass
|  |  |  | TC_LG_002 | Pass
|  |  |  | TC_LG_003 | Blocked
|  |  |  | TC_LG_004 | Pass
|  |  |  | TC_LG_005 | Pass
|  |  |  | TC_LG_006 | Pass
|  |  |  | TC_LG_007 | Blocked
|  |  |  | TC_LG_008 | Pass
|  |  |  | TC_LG_009 | Blocked
|  |  |  | TC_LG_010 | Pass
1.4 | Forgot Password | TS_004 | Validate the working of Forgot Password functionality | TC_FP_001 | Blocked
|  |  |  | TC_FP_002 | Blocked
|  |  |  | TC_FP_003 | Blocked
|  |  |  | TC_FP_004 | Blocked
|  |  |  | TC_FP_005 | Blocked
|  |  |  | TC_FP_006 | Blocked
|  |  |  | TC_FP_007 | Blocked
|  |  |  | TC_FP_008 | Blocked
|  |  |  | TC_FP_009 | Blocked
|  |  |  | TC_FP_010 | Blocked
|  |  |  | TC_FP_011 | Blocked
|  |  |  | TC_FP_012 | Blocked
|  |  |  | TC_FP_013 | Blocked
|  |  |  | TC_FP_014 | Blocked
|  |  |  | TC_FP_015 | Blocked
|  |  |  | TC_FP_016 | Blocked
|  |  |  | TC_FP_017 | Blocked
|  |  |  | TC_FP_018 | Blocked
|  |  |  | TC_FP_019 | Blocked
|  |  |  | TC_FP_020 | Blocked
|  |  |  | TC_FP_021 | Blocked
|  |  |  | TC_FP_022 | Blocked
|  |  |  | TC_FP_023 | Blocked
|  |  |  | TC_FP_024 | Blocked
|  |  |  | TC_FP_025 | Blocked
1.5 | Search Product | TS_005 | Validate the working of Search functionality | TC_SF_001 | Pass
|  |  |  | TC_SF_002 | Pass
|  |  |  | TC_SF_003 | Pass
|  |  |  | TC_SF_004 | Pass
|  |  |  | TC_SF_005 | Pass
|  |  |  | TC_SF_006 | Pass
|  |  |  | TC_SF_007 | Pass
|  |  |  | TC_SF_008 | Pass
|  |  |  | TC_SF_009 | Pass
|  |  |  | TC_SF_010 | Pass
|  |  |  | TC_SF_011 | Pass
|  |  |  | TC_SF_012 | Pass
|  |  |  | TC_SF_013 | Pass
|  |  |  | TC_SF_014 | Pass
|  |  |  | TC_SF_015 | Pass
|  |  |  | TC_SF_016 | Pass
|  |  |  | TC_SF_017 | Pass
|  |  |  | TC_SF_018 | Pass
|  |  |  | TC_SF_019 | Pass
|  |  |  | TC_SF_020 | Pass
|  |  |  | TC_SF_021 | Blocked
|  |  |  | TC_SF_022 | Pass
1.6 | Product Compare | TS_006 | Validate the working of Product Compare functionality | TC_PC_001 | Pass
|  |  |  | TC_PC_002 | Pass
|  |  |  | TC_PC_003 | Pass
|  |  |  | TC_PC_004 | Pass
|  |  |  | TC_PC_005 | Pass
|  |  |  | TC_PC_006 | Blocked
|  |  |  | TC_PC_007 | Pass
|  |  |  | TC_PC_008 | Pass
|  |  |  | TC_PC_009 | Pass
|  |  |  | TC_PC_010 | Pass
|  |  |  | TC_PC_011 | Pass
|  |  |  | TC_PC_012 | Pass
|  |  |  | TC_PC_013 | Pass
|  |  |  | TC_PC_014 | Pass
|  |  |  | TC_PC_015 | Pass
|  |  |  | TC_PC_016 | Pass
|  |  |  | TC_PC_017 | Pass
|  |  |  | TC_PC_018 | Pass
|  |  |  | TC_PC_019 | Pass
|  |  |  | TC_PC_020 | Pass
|  |  |  | TC_PC_021 | Pass
|  |  |  | TC_PC_022 | Pass
|  |  |  | TC_PC_023 | Blocked
|  |  |  | TC_PC_024 | Pass
1.7 | Product Display | TS_007 | Validate the working of Display page functionality for the diffrent types of products | TC_PDP_001 | Pass
|  |  |  | TC_PDP_002 | Pass
|  |  |  | TC_PDP_003 | Pass
|  |  |  | TC_PDP_004 | Pass
|  |  |  | TC_PDP_005 | Pass
|  |  |  | TC_PDP_006 | Fail | DEF_008 | Open
|  |  |  | TC_PDP_007 | Blocked
|  |  |  | TC_PDP_008 | Pass
|  |  |  | TC_PDP_009 | Pass
|  |  |  | TC_PDP_010 | Pass
|  |  |  | TC_PDP_011 | Pass
|  |  |  | TC_PDP_012 | Pass
|  |  |  | TC_PDP_013 | Pass
|  |  |  | TC_PDP_014 | Pass
|  |  |  | TC_PDP_015 | Pass
|  |  |  | TC_PDP_016 | Pass
|  |  |  | TC_PDP_017 | Pass
|  |  |  | TC_PDP_018 | Pass
|  |  |  | TC_PDP_019 | Pass
|  |  |  | TC_PDP_020 | Blocked
|  |  |  | TC_PDP_021 | Blocked
|  |  |  | TC_PDP_022 | Pass
|  |  |  | TC_PDP_023 | Pass
|  |  |  | TC_PDP_024 | Pass
|  |  |  | TC_PDP_025 | Pass
|  |  |  | TC_PDP_026 | Pass
|  |  |  | TC_PDP_027 | Pass
|  |  |  | TC_PDP_028 | Blocked
|  |  |  | TC_PDP_029 | Pass
|  |  |  | TC_PDP_030 | Pass
|  |  |  | TC_PDP_031 | Pass
|  |  |  | TC_PDP_032 | Pass
|  |  |  | TC_PDP_033 | Pass
|  |  |  | TC_PDP_034 | Blocked
|  |  |  | TC_PDP_035 | Pass
|  |  |  | TC_PDP_036 | Blocked
|  |  |  | TC_PDP_037 | Pass
1.8 | Add to cart | TS_008 | Validate the working of 'Add to Cart' functionality | TC_ATC_001 | Pass
|  |  |  | TC_ATC_002 | Pass
|  |  |  | TC_ATC_003 | Pass
|  |  |  | TC_ATC_004 | Pass
|  |  |  | TC_ATC_005 | Pass
|  |  |  | TC_ATC_006 | Pass
|  |  |  | TC_ATC_007 | Pass
|  |  |  | TC_ATC_008 | Blocked
|  |  |  | TC_ATC_009 | Pass
1.9 | WishList | TS_009 | Validate the WishList functionality | TC_WL_001 | Pass
|  |  |  | TC_WL_002 | Pass
|  |  |  | TC_WL_003 | Pass
|  |  |  | TC_WL_004 | Pass
|  |  |  | TC_WL_005 | Pass
|  |  |  | TC_WL_006 | Pass
|  |  |  | TC_WL_007 | Pass
|  |  |  | TC_WL_008 | Pass
|  |  |  | TC_WL_009 | Pass
|  |  |  | TC_WL_010 | Pass
|  |  |  | TC_WL_011 | Pass
|  |  |  | TC_WL_012 | Pass
|  |  |  | TC_WL_013 | Pass
|  |  |  | TC_WL_014 | Pass
|  |  |  | TC_WL_015 | Pass
|  |  |  | TC_WL_016 | Pass
|  |  |  | TC_WL_017 | Fail
|  |  |  | TC_WL_018 | Blocked
|  |  |  | TC_WL_019 | Blocked
|  |  |  | TC_WL_020 | Blocked
|  |  |  | TC_WL_021 | Blocked
2 | Shopping cart | TS_010 |  | TC_SC_01 | Pass
|  |  |  | TC_SC_02 | Pass
|  |  |  | TC_SC_03 | Pass
|  |  |  | TC_SC_04 | Pass
|  |  |  | TC_SC_05 | Pass
|  |  |  | TC_SC_06 | Pass
|  |  |  | TC_SC_07 | Fail | DEF_011 | Open
|  |  |  | TC_SC_08 | Pass
|  |  |  | TC_SC_09 | Pass
|  |  |  | TC_SC_10 | Pass
|  |  |  | TC_SC_11 | Pass
|  |  |  | TC_SC_12 | Pass
|  |  |  | TC_SC_13 | Pass
|  |  |  | TC_SC_14 | Pass
|  |  |  | TC_SC_15 | Pass
|  |  |  | TC_SC_16 | Pass
|  |  |  | TC_SC_17 | Pass
|  |  |  | TC_SC_18 | Blocked
|  |  |  | TC_SC_19 | Blocked
|  |  |  | TC_SC_20 | Blocked
|  |  |  | TC_SC_21 | Blocked
|  |  |  | TC_SC_22 | Blocked
|  |  |  | TC_SC_23 | Pass
|  |  |  | TC_SC_24 | Blocked
|  |  |  | TC_SC_25 | Pass
|  |  |  | TC_SC_26 | Blocked
|  |  |  | TC_SC_27 | Blocked
|  |  |  | TC_SC_28 | Blocked
|  |  |  | TC_SC_29 | Blocked
|  |  |  | TC_SC_30 | Blocked
|  |  |  | TC_SC_31 | Pass
|  |  |  | TC_SC_32 | Blocked
|  |  |  | TC_SC_33 | Blocked
2 | Home page | TS_011 | Validate the working of Home Page Functionality | TC_HP_001 | Pass
|  |  |  | TC_HP_002 | Blocked
|  |  |  | TC_HP_003 | Pass
|  |  |  | TC_HP_004 | Pass
|  |  |  | TC_HP_005 | Pass
|  |  |  | TC_HP_006 | Pass
|  |  |  | TC_HP_007 | Pass
|  |  |  | TC_HP_008 | Pass
|  |  |  | TC_HP_009 | Blocked
|  |  |  | TC_HP_010 | Pass
2.1 | My Account | TS_012 | Validate the working of My Account functionality | TC_MA_001 | Pass
|  |  |  | TC_MA_002 | Pass
|  |  |  | TC_MA_003 | Pass
|  |  |  | TC_MA_004 | Pass
|  |  |  | TC_MA_005 | Pass
|  |  |  | TC_MA_006 | Pass
|  |  |  | TC_MA_007 | Blocked
|  |  |  | TC_MA_008 | Pass
2.2 | Account Information | TS_013 | Account Information | TC_MAI_001 | Pass
|  |  |  | TC_MAI_002 | Pass
|  |  |  | TC_MAI_003 | Pass
|  |  |  | TC_MAI_004 | Pass
|  |  |  | TC_MAI_005 | Pass
|  |  |  | TC_MAI_006 | Pass
|  |  |  | TC_MAI_007 | Pass
|  |  |  | TC_MAI_008 | Fail | 'DEF_007 | Open
|  |  |  | TC_MAI_009 | Pass
|  |  |  | TC_MAI_010 | Pass
|  |  |  | TC_MAI_011 | Pass
|  |  |  | TC_MAI_012 | Pass
|  |  |  | TC_MAI_013 | Pass
2.3 | Change Password | TS_015 | Validate the working of My Account > 'Change Password functionality | TC_CP_001 | Pass
|  |  |  | TC_CP_002 | Pass
|  |  |  | TC_CP_003 | Pass
|  |  |  | TC_CP_004 | Pass
|  |  |  | TC_CP_005 | Pass
|  |  |  | TC_CP_006 | Pass
|  |  |  | TC_CP_007 | Pass
|  |  |  | TC_CP_008 | Pass
|  |  |  | TC_CP_009 | Blocked
|  |  |  | TC_CP_010 | Pass
|  |  |  | TC_CP_011 | Pass
|  |  |  | TC_CP_012 | Blocked
|  |  |  | TC_CP_013 | Pass
2.4 | Address Book | TS_016 | Validate the working of My Account > 'Address Book functionality | TC_AB_001 | Pass
|  |  |  | TC_AB_002 | Pass
|  |  |  | TC_AB_003 | Pass
|  |  |  | TC_AB_004 | Pass
|  |  |  | TC_AB_005 | Pass
|  |  |  | TC_AB_006 | Fail | DEF_001 | Open
|  |  |  | TC_AB_007 | Pass
|  |  |  | TC_AB_008 | Blocked
|  |  |  | TC_AB_009 | Pass
|  |  |  | TC_AB_010 | Pass
|  |  |  | TC_AB_011 | Pass
|  |  |  | TC_AB_012 | Pass
|  |  |  | TC_AB_013 | Pass
|  |  |  | TC_AB_014 | Pass
|  |  |  | TC_AB_015 | Pass
|  |  |  | TC_AB_016 | Blocked
|  |  |  | TC_AB_017 | Pass
|  |  |  | TC_AB_018 | Pass
|  |  |  | TC_AB_019 | Pass
|  |  |  | TC_AB_020 | Blocked
|  |  |  | TC_AB_021 | Blocked
2.5 | Order History | TS_017 | Validate the working of 'Newsletter' functionality | TC_NLT_001 | Pass
|  |  |  | TC_NLT_002 | Pass
|  |  |  | TC_NLT_003 | Pass
|  |  |  | TC_NLT_004 | Pass
|  |  |  | TC_NLT_005 | Pass
|  |  |  | TC_NLT_006 | Pass
|  |  |  | TC_NLT_007 | Pass
|  |  |  | TC_NLT_008 | Pass
|  |  |  | TC_NLT_009 | Pass
|  |  |  | TC_NLT_010 | Blocked
|  |  |  | TC_NLT_011 | Pass
|  |  |  | TC_NLT_012 | Pass
2.6 | Affiliate Functionality | TS_018 | Validate the working of 'Affiliate Account' functionality | TC_AF_001 | Pass
|  |  |  | TC_AF_002 | Blocked
|  |  |  | TC_AF_003 | Pass
|  |  |  | TC_AF_004 | Pass
|  |  |  | TC_AF_005 | Pass
|  |  |  | TC_AF_006 | Fail | 'DEF_002 | Open
|  |  |  | TC_AF_007 | Pass
|  |  |  | TC_AF_008 | Fail | DEF_003 | Open
|  |  |  | TC_AF_009 | Pass
|  |  |  | TC_AF_010 | Pass
|  |  |  | TC_AF_011 | Pass
|  |  |  | TC_AF_012 | Pass
|  |  |  | TC_AF_013 | Pass
|  |  |  | TC_AF_014 | Blocked
|  |  |  | TC_AF_015 | Pass
|  |  |  | TC_AF_016 | Blocked
|  |  |  | TC_AF_017 | Pass
2.7 | News Letter | TS_019 | Validate the working of 'News Letter' functionality | TC_NLT_001 | Pass
|  |  |  | TC_NLT_002 | Pass
|  |  |  | TC_NLT_003 | Pass
|  |  |  | TC_NLT_004 | Pass
|  |  |  | TC_NLT_005 | Pass
|  |  |  | TC_NLT_006 | Pass
|  |  |  | TC_NLT_007 | Pass
|  |  |  | TC_NLT_008 | Pass
|  |  |  | TC_NLT_009 | Pass
|  |  |  | TC_NLT_010 | Pass
|  |  |  | TC_NLT_011 | Pass
|  |  |  | TC_NLT_012 | Blocked
|  |  |  | TC_NLT_013 | Pass
2.8 | Contact Us | TS_027 | Validate the working of 'Contact Us' functionality | TC_CU_001 | Blocked
|  |  |  | TC_CU_002 | Pass
|  |  |  | TC_CU_003 | Pass
|  |  |  | TC_CU_004 | Pass
|  |  |  | TC_CU_005 | Pass
|  |  |  | TC_CU_006 | Fail | DEF_004 | Open
|  |  |  | TC_CU_007 | Pass
|  |  |  | TC_CU_008 | Pass
|  |  |  | TC_CU_009 | Fail | DEF_005 | Open
|  |  |  | TC_CU_010 | Pass
|  |  |  | TC_CU_011 | Pass
|  |  |  | TC_CU_012 | Blocked
|  |  |  | TC_CU_013 | Fail
2.9 | Gift Certificate | TS_028 | Validate the working of 'Gift Certificate' functionality | TC_GC_001 | Pass
|  |  |  | TC_GC_002 | Pass
|  |  |  | TC_GC_003 | Fail
|  |  |  | TC_GC_004 | Pass
|  |  |  | TC_GC_005 | Pass
|  |  |  | TC_GC_006 | Pass
|  |  |  | TC_GC_007 | Pass
|  |  |  | TC_GC_008 | Pass
3 | Special Offers | TS_029 | Validate the working of 'Special Offers' functionality | TC_SO_001 | Pass
|  |  |  | TC_SO_002 | Pass
|  |  |  | TC_SO_003 | Pass
|  |  |  | TC_SO_004 | Blocked
|  |  |  | TC_SO_005 | Pass
|  |  |  | TC_SO_006 | Pass
|  |  |  | TC_SO_007 | Blocked
|  |  |  | TC_SO_008 | Pass
|  |  |  | TC_SO_009 | Blocked
|  |  |  | TC_SO_010 | Blocked
|  |  |  | TC_SO_011 | Blocked
|  |  |  | TC_SO_012 | Pass
|  |  |  | TC_SO_013 | Blocked
|  |  |  | TC_SO_014 | Pass
|  |  |  | TC_SO_015 | Pass
|  |  |  | TC_SO_016 | Blocked
3.1 | Header Footer | TS_030 | Validate the working of 'Header Footer' functionality | TC_HF_001 | Pass
|  |  |  | TC_HF_002 | Pass
|  |  |  | TC_HF_003 | Pass
|  |  |  | TC_HF_004 | Pass
|  |  |  | TC_HF_005 | Pass
|  |  |  | TC_HF_006 | Pass
|  |  |  | TC_HF_007 | Pass
|  |  |  | TC_HF_008 | Pass
|  |  |  | TC_HF_009 | Pass
|  |  |  | TC_HF_010 | Pass
|  |  |  | TC_HF_011 | Pass
|  |  |  | TC_HF_012 | Pass
|  |  |  | TC_HF_013 | Pass
|  |  |  | TC_HF_014 | Pass
|  |  |  | TC_HF_015 | Pass
|  |  |  | TC_HF_016 | Pass
|  |  |  | TC_HF_017 | Pass
|  |  |  | TC_HF_018 | Pass
|  |  |  | TC_HF_019 | Blocked
|  |  |  | TC_HF_020 | Pass
3.2 | Different Currencies | TS_031 | Validate the complete Application functionality for different currencies | TC_CR_001 | Pass
|  |  |  | TC_CR_002 | Pass
|  |  |  | TC_CR_003 | Pass

## Summary Report
Project Name: | Tutorial-Ninja | SUMMARY
Project ID: | / | Total Test Cases | 293
Application ID/Name: | Tutorial-Ninja | Executed | 293
From Report Date: | / | Pass | 279
Report Date: | / | Fail | 14
Completed By: | Sumit Rane | Not Executed | 0
Manager: | /
QA Manager: | /